## qry_TechTransferCompliance
ClientName | TargetMoleculeType | MilestoneName | Soll_Date | Completed_Date | Status | Days_Overdue | Risk_Level
NexaBiologics | Nanobody (VHH) | Raw Material Sourcing | 2026-01-25 | 2026-01-24 | Completed |  | #Error
NexaBiologics | Nanobody (VHH) | Analytics Method Verification | 2026-02-15 | 2026-02-14 | Completed |  | #Error
NexaBiologics | Nanobody (VHH) | SOP Approval for Fermentation | 2026-03-01 | 2026-02-28 | Completed |  | #Error
VaxCore Therapeutics | Plasmid DNA (pDNA) | Raw Material Sourcing | 2026-02-20 | 2026-03-12 | Completed (Delayed) |  | #Error
VaxCore Therapeutics | Plasmid DNA (pDNA) | Analytics Method Verification | 2026-03-20 | 2026-03-25 | Completed |  | #Error
VaxCore Therapeutics | Plasmid DNA (pDNA) | SOP Approval for Fermentation | 2026-04-10 | 2026-04-08 | Completed |  | #Error
AlveoPharma | Recombinant Protein | Raw Material Sourcing | 2026-04-01 | 2026-03-29 | Completed |  | #Error
AlveoPharma | Recombinant Protein | Analytics Method Verification | 2026-05-01 | 2026-05-05 | Completed |  | #Error
AlveoPharma | Recombinant Protein | SOP Approval for Fermentation | 2026-06-15 |  | In Progress (Overdue) |  | #Error
BioThera GmbH | Antigen Vaccine | Raw Material Sourcing | 2026-05-01 | 2026-04-28 | Completed |  | #Error
BioThera GmbH | Antigen Vaccine | Analytics Method Verification | 2026-06-20 |  | In Progress |  | #Error
BioThera GmbH | Antigen Vaccine | SOP Approval for Fermentation | 2026-07-15 |  | Not Started |  | #Error