## tbl_Milestones
MilestoneID | ProjectID_FK | MilestoneName | Soll_Date | Completed_Date | Status
1 | 1 | Raw Material Sourcing | 2026-01-25 | 2026-01-24 | Completed
2 | 1 | Analytics Method Verification | 2026-02-15 | 2026-02-14 | Completed
3 | 1 | SOP Approval for Fermentation | 2026-03-01 | 2026-02-28 | Completed
4 | 2 | Raw Material Sourcing | 2026-02-20 | 2026-03-12 | Completed (Delayed)
5 | 2 | Analytics Method Verification | 2026-03-20 | 2026-03-25 | Completed
6 | 2 | SOP Approval for Fermentation | 2026-04-10 | 2026-04-08 | Completed
7 | 3 | Raw Material Sourcing | 2026-04-01 | 2026-03-29 | Completed
8 | 3 | Analytics Method Verification | 2026-05-01 | 2026-05-05 | Completed
9 | 3 | SOP Approval for Fermentation | 2026-06-15 |  | In Progress (Overdue)
10 | 4 | Raw Material Sourcing | 2026-05-01 | 2026-04-28 | Completed
11 | 4 | Analytics Method Verification | 2026-06-20 |  | In Progress
12 | 4 | SOP Approval for Fermentation | 2026-07-15 |  | Not Started